## LINKS
INDEX
MMD ICERTIS
MMD QA | https://accentureqa.icertis.com/
MMD PRODFIX | https://accentureprdfix.icertis.com/Dashboard
MMD PRODUCTION | https://accenture.icertis.com/#
BSR E2E
E2E ¦ SBOX LIVE
E2E ¦ SBOX 1
E2E ¦ SBOX 4
E2E ¦ SBOX 7
E2E ¦ SBOX 11
BSR SNOW
SNOW ¦ SBOX LIVE
SNOW ¦ SBOX 1
SNOW ¦ SBOX 4
SNOW ¦ SBOX 7
SNOW ¦ SBOX 11
MMD FILES
TEST PLAN | TEST PLAN
TEST PLAN TRACKER | FY25.3 Test Plan Tracker
TIMELINE | MMD June Release Timeline
BUG SUMMARY | FY25 iCertis_Buy Side_Bug Summary
CAPACITY PLAN | FY25.3 Capacity Plan
FY25 Stand-Up Meeting MMD Test Team | FY25 Stand-Up Meeting MMD Test Team
FY25 MMD Buy Side Tracker | FY25 MMD Buy Side Tracker
AZURE DEVOPS | ADO
WORKBOOK
AUTOMATION
AUTOMATION | Automation
H+M Collateral List | H+M Collateral List
AUTOMATION PAJ | FY25 Automation APAJ.xlsx
INTELLIGENT AUTOMATION | https://intelligentautomationcoe.accenture.com/view-plan
AUTOMATION TRACKER | FY25 MMD Automation Tracker.xlsx
NAB GROUPS
AD Group | Purpose
MMD.BuySide.Program | Distribution group for the entire MMD Buyside Program Team (Delivery Lead, FA, BA, TA, Test and Automation Team)
MMD.BuySide.Program.FA.BA | Distribution group for MMD Buyside Program FAs and BAs (Functional Architects and Business Architects)
MMD.BuySide.Program.TestAndAutomation | Distribution group for MMD Buyside Program Test and Automation Team
MMD.BuySide.Program.Stab.Support | Distribution group for MMD Buyside Stabilization Support Team
@CIO.ProcPlus.ServiceNowL2Ops. | BSR Support
#VALUE! | MMPR
CIO.MMD.Operations | Distribution group for MMD Buyside Operations Team

## BuySide POC
Activity | Task | POC | Back-Up | Comment
Timeline Downtime Lead | - Get the list of downtime schedule for this release (anusha) - Inform the testers/FA and MMD Team when downtime starts and ends - List down the duration of each downtime in the Downtime Tab -Need to loop BSR Team for awareness purpose (if not Cced in email) | Jhea | Astha | MMD Downtime Log CIO.ProcPlus.ServiceNowL2Ops <CIO.ProcPlus.ServiceNowL2Ops@accenture.com>
Sprint Lead | - Organize and lead the Sprint TCER Review for Test Lead, FA Lead and Business - Request Sign-off from FA Lead and Business (Ligia, Bhumika/Benj) - Assign testers responsible for execution of every TCER - Upload the TCERs in ADO Userstory and Update the state status. - Review Overall TCER | SP 15 - Jonathan SP 16 - Guna SP 17 - Astha SP 18 - Izzy | SP 15 - Jho SP 16 - Jonathan SP 17 - Guna SP 18 - Jho
UAT Support / UAT Kick off Lead (QA) | - Request the list of UAT participants from the Business team (Ligia, Bhumika/Benj) - Request KT from Change Management (applicable for first-time participants max of (4); coordinate and confirm with FAs if needed) - Create the UAT framework - Schedule a UAT framework review meeting with the Test Lead, FA, and Business to discuss the high-level approach - Obtain UAT framework sign-off from the Test Lead, FA, and Business - Request QA environment access for UAT participants (Rudra/Fina) - Organize and lead UAT kick-off sessions (Session 1 and Session 2) - Align with your backup to ensure coverage during SL/VL - Schedule UAT checkpoint meetings - Guide participants during execution - Send daily status reports - After UAT execution, request business sign-off (Ligia, Bhumika and Benj) - Ensure all testing is completed before release | KTLO/TPRM - Arianne REINVENTION AI - Ele | KTLO/TPRM - Jonathan REINVENTION AI - Jho
Data Conversion Lead | - Create inflight data in Prodfix (Mock Run 1) - Request for extracted data in Prodfix and populate/highlight needed values (Ask Rudra/Fina Dev for the extract file) - Participate on the discussion from FA to Business for the scope of Data conversion; sometime we include it during sprint review. - Organize and lead the discussion of included attributes with the Business - Validate if data is reflecting correctly afte ES Sync (Mock Run 2) - Check created inflight req/agreements if changes reflected - Repeat the steps above for Production - After test, request business signoff - During cut over send validation completion | DC - Jhea | DC - Jonathan
TPRM/Coupa Lead | - Organize and Create Test Scripts for TPRM User Stories - Requesting of Test Data of Coupa ID to Coupa Team (User Stories) - Requesting of Test Data of Coupa ID to Coupa Team (Smoke Testing) - Validating of E2E Integration coupa to mmd - Data Conversion Regarding TPRM User Stories (Output and ES Sync File - Creating of Inflight Data in PRDFIX (Mock 2) - MMD TPRM UAT (Refer to this cell (UAT Support / UAT Kick off Lead (QA)) - Support TPRM UAT | Guna | Jonathan
Mock - Cutover Test (PRODFIX) Lead | - Create Mock Test TCER - Organize and lead the Mock/Smoke Test TCER Review for Test Lead, FA Lead and Business - Request Mock/Smoke TCER signoff from FA/Business - Request BSR and Synops repoint environment to Prodfix - Request Prodfix access for involved testers and Email Override - Assign testers responsible for execution of every scenario - Send daily status report during mock test execution - After Mock test, send overall completion email - If there are bugs/issues, once fixed and retested, and if there is additional or changes from the approved scenario, need to send another completion email to inform FA/Biz/Dev | Jhea | Jho
Smoke/Cutover Test Lead | - Create Smoke Test TCER (or reuse the Mock Test TCER) - Organize and lead the Smoke Test TCER Review for Test Lead, FA Lead and Business (already covered in Mock Test Prep) - Request Smoke Test signoff from Business if there are additional or major changes with the test coverage from Mock to Smoke Test - Request support from other involved teams (BSR, Synops, Coupa, MMPR, etc.) including contact numbers (c/o Cutover Lead) - Confirm the MMD Participant and request to test Production Access as well - Plot the date and timing of Icertis Write Test (1st BSR/Synops activity) and Smoke Test Execution (2nd BSR/Synops activity) - Inform the Cutover lead on the BSR, Synops, IH, TPRM and MMD Team's list of names, contact numbers and access needed - Request Production access for involved testers and Email Override (Inform Diego and Anusha) - Organize and lead the Support Call for Smoke Test (create Teams GC including all the cutover support Dev/FA/Test/TPRM/IH/Synops/BSR) - Create group chats in social media (messenger) and MS Teams - Assign testers responsible for execution of every scenario - -Attend the Cutover checkpoints every 4 hours and asks if activities are on-track (Need back up) -Coordinate with MMD Test and BSR Team if activities are on-track or not -Provide updates to all group convo and to the Cutover Lead (Diego) | Tin | Jho
Automation Lead | -Discuss the assigned AT tasks (updates, concerns) -Update the 'Automation Detailed Plan' file -Prioritize the regression and PT scripts to be Automated -TBD: Send weekly status report for AT -Create framework for the needed AT scripts | Jho
Cutover Back-up Test Lead | -Attend the Cutover checkpoints every 4 hours and asks if activities are on-track -Coordinate with MMD Test and BSR Team if activities are on-track or not -Provide updates to all group convo and to the Cutover Lead (Diego) | Jho
MMD Test Mgnt. Lead | -Overall management of the MMD Buyside Testing Team -Reviews everything within the team -Submits the needed Admin tasks for the team | Tin | Jho

## TCER
TCER Assignee | Assigned Testers | Sprint | User Story ID | Category | Requirement Name (High Level) | Status | TCER | Positive Scenario (based on requirement) | In-flight Scenario | Negative Scenario | Regression | Comment | FA Comments | Business comments
Jonathan | Arianne | 15 | 611512 | KTLO | Hide "Edit in Office for the Web" when status is "Ready For Signature" | Completed Execution Review | TC-MMD_BuySide_R26.3_S15_611512_[KTLO_BuySide]_Edit in Office for the Web when status is Ready For Signature | Type: SMA, SCC, SSW • Validation of visibility of "Edit in Office for the web" on three dots icon in different business statuses (In Progress, Review In Progress, Awaiting Approval, Ready for Signature) • Validation that “Edit in Office for the Web” is hidden when the agreement reaches Ready for Signature status across all action menus • Validation that “Edit in Office for the Web” becomes available again when the agreement transitions back to an editable status • Validation of document edit behavior when downloading and re‑uploading a modified template in Ready for Signature status • Validation of document version increment upon uploading a modified template in Ready for Signature status • Validation that document status and version remain unchanged when a downloaded template is uploaded without modifications - Direct Creation of SMA, SCC, SSW until executed status
|  | 15 | 854801 | KTLO | [Effort] [Feedback] Optional Notes for Signing Reason in the Console (Adobe) | Not Applicable | [5 empty] | No Action for Test Team
Jhea | Elealeh, Astha, Izzy | 15 | 858074 | KTLO | [CHG] [FEEDBACK] Additional Dropdown option for Supplier Preferred Name | Completed Execution Review | TC-MMD BuySide R26.3 S15 858074 [KTLO] [CHG] [FEEDBACK] Additional Dropdown option for Supplier Preferred Name.xlsx | Type: SMA, SSW, SCC • Validation of the additional dropdown options for Supplier Preferred Name should be selectable. Additional dropdown options: -Agency -Authorized Distributor -Buyer -Contracting Party -Contractor -Customer -Distributor -Independent Contractor -Licensee -Licensor -Managed Service Provider (MSP) -Manufacturer -Merchant -Producer -Publisher -Retailer -Seller -Service PRovider -Staffing Agency -Subcontractor -Systems Integrator -Temp Agency -Wholesaler • Validation of the accurate expected value when clicking the lookup search • Validation of the accuracy and alphabetical order of expected values when downloading the export file from the lookup search: -Advisor -Agency -Agent -Artist -Authorized Distributor -BDA -Beneficiary -Buyer -Consultant -Contracting Party -Contractor -Customer -Distributor -Expert -Grantee -Independent Contractor -Lessor -License -Licensee -Licensor -Luminary -Managed Service Provider (MSP) -Manufacturer -Merchant -Partner -Producer -Production House -Provider -Publisher -Purchaser -Retailer -Seller -Service PRovider -Speaker -Sponsor -Staffing Agency -Subcontractor -Supplier -Systems Integrator -Temp Agency -Vendor -Wholesaler • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause. |  | Type: SMA, SSW, SCC • Validation of updating the Supplier Preferred Name from default "Provider" to Advisor during the agreement's ‘In Progress’ state. • Validation of updating the Supplier Preferred Name from Agent to Expert during the agreement's 'In Progress' state. | Type: SMA, SSW, SCC • Validation of old values remaining selectable and correctly inherited on the Summary Details page. -Agent -Advisor -Artist -BDA -Beneficiary -Consultant -Expert -Grantee -Lessor -License -Luminary -Partner -Production House -Provider -Purchaser -Speaker -Sponsor -Supplier -Vendor • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause. | [Jho] - we need inflight scenario
Jonathan | Guna | 15 | 1041077 | BUG | [MMD BuySide][R26.2 QA, PRDFIX] - Excess signatory is showing in the signatory field | Completed Execution Review | TC-MMD_BuySide_R26.3_S15_1041077_[KTLO] [MMD BuySide][R26.2 QA, PRDFIX] - Excess signatory is showing in the signatory field | Type: SMA, SCC, SSW • Validation of: correct signatory configuration behavior, ensuring the selected number of internal and external signatories remains accurate and editable when navigating forward and backward in the workflow. (In creation, In Progress, Ready for Signature). - Direct Creation of SMA, SCC, SSW until executed status |  |  | Type: SMA, SCC, SSW • Validation of: the correct triggering and non‑triggering of conditions for Signatory 3–15 and internal and external witness signatories. (In creation, In Progress, Ready for Signature). - Direct Creation of SMA, SCC, SSW until executed status
Jonathan | Arianne | 15 | 1044636 | BUG | [Buy Side R26.2 S14] - Supplier Permitted Termination Date is not updating in Save Search in agreement list | Completed Execution Review | TC-MMD_BuySide_R26.3_S15_1044636_[KTLO]_[Buy Side R26.2 S14] - Supplier Permitted Termination Date is not updating in Save Search in agreement list | Type: SCC • Validation of the Supplier Permitted Termination Date automatically increase by one day and not increasingby one in different statuses in agreement and saved search. • Validation of: the accurate calculation of the Supplier Permitted Termination Date derived from the date variance between the Inherited Document Effective Date and the Contract Change Effective Date. - Direct creation of SCC in In Progress until Executed Status - Direct creation of SCC until Awaiting Approval Status - Direct creation of SCC until Ready for Signature Status - Direct creation of SCC until Awaiting Signature Status - Direct creation of SCC until Executed Status | Type: SCC • Validation of the Supplier Permitted Termination Date automatically increase by one day and not increasingby one in different statuses in agreement and saved search. • Validation of: the accurate calculation of the Supplier Permitted Termination Date derived from the date variance between the Inherited Document Effective Date and the Contract Change Effective Date. - Direct creation of SCC in In Progress until Executed Status - Direct creation of SCC until Awaiting Approval Status - Direct creation of SCC until Ready for Signature Status - Direct creation of SCC until Awaiting Signature Status
Guna | Jhea | 15 | 1053552 | TPRM | [TPRM Initiative][Functional] Unhide Unknown option in DOJ prohibited countries attribute in MMD | Completed Execution Review | TC-MMD_BuySide_R26.3_S15_1053552 [TPRM] [Functional] Unhide Unknown option in DOJ prohibited countries attribute in MMD.xlsx | Type: SREQ, SMA, SCC, SSW • Validation of the list of dropdown values for DOJ Prohibited Countries attribute. • Validation of visibility of 'Unknown' option should be selectable in MMD. All validations and rules update will be tested with the following - Direct Creation of SREQ request - Direct Creation of Agreements (SMA, SCC, SSW) - Creation from SREQ request to Agreement until Executed status | Type: SREQ / SMA • Inflight - Check for "Unknown" value from attribute dropdown - DOJ Prohibited Countries
Guna | Jonathan | 15 | 1053553 | TPRM | [TPRM Initiative][Technical] Update Coupa mapping for Unknown option in DOJ prohibited countries attribute in MMD | Completed Execution Review | TC-MMD_BuySide_R26.3_S15_1053553 [TPRM][Technical] Update Coupa mapping for Unknown option in DOJ prohibited countries attribute in MMD.xlsx | Coupa ---> MMD Type: SREQ, SMA, SCC, SSW • Validation of the list of dropdown values of DOJ Prohibited Countries attribute which is integrated using Coupa ID. • Validation of visibility of 'Unknown' option which is integrated between Coupa and MMD. All validations and rules update will be tested with the following, - Direct Creation of SREQ request - Direct Creation of Agreements (SMA, SCC, SSW) - Creation from SREQ request to Agreement until Executed status
Guna | Astha | 16 | 999805 | BUG | [Buy][R26.2] Multiple “Waiting for Approval – In Editing” statuses displayed instead of a single one | Not Applicable | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1075154 | Type: SMA, SCC, SSW • Validation of Single Business Status "Awaiting for Approval - In Editing" displayed in Agreement dashboard. • No duplicate business status for “Awaiting for Approval – In Editing” should appear in filter options. - Direct Creation of SMA, SCC, SSW until "Awaiting for Approval - In Editing" status |  |  |  | 20/4 - This is an invalid bug and both the status are different and getting reflected back in SynOps - waiting for the confirmation from Deepak and Jof 21/4 - Upon discussion the bug will be rejected
Elealeh | Arianne | 16 | 1061641 | BUG | [MMD BuySide][R26.3] Attribute Value discrepancy for "Is Contract Admin Present" for business status Assigned or Assignment Pending is displayed in Saved Search | Completed Execution Review | TC-MMD_BuySide_R26.3_S16_1061641_[MMD BuySide][R26.3] Attribute Value discrepancy for 'Is Contract Admin Present' for business status Assigned or Assignment Pending is displayed in Saved Search | BSR ¦ SREQ • Validation that the Contract Admin attribute value is visible in the SREQ after submission. • Validation that the “Is Contract Admin Present” attribute appears with the correct (Yes/Blank) value in saved search results. • Validation that the agreement type (Internal Project, Go To Market Offering, Single Client) aligns correctly with the workflow state. • Validate that the contract admin is present if the status is assigned & assignment pending and validate that the "Is contract Admin Present" has a value in the save search. | • Validation that the “is contract Admin Present” attribute appears with the correct value (Yes/Blank) in the save search. | • Create request and remove the contract admin then validate the value in the save search.
Jonathan | Izzy | 16 | 186157 | KTLO | Create Read-only role for Rules, clauses and templates in QA, Prodfix, Prod | Not Applicable | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1076912 | • Validation that users assigned to the new security group have view‑only access to rules, allowing them to view rule details and audit logs without the ability to edit the rules. • Validation that users in the new security group can download the Word version of templates and clauses. • Validation that users in the new security group are restricted from editing or terminating templates and clauses after downloading. • Validation that users assigned to the new MMD Template Management Stream security group, either alone or in combination with Procurement, Legal, Business, Delegated Spend, or Buyside Leadership security groups, have view‑only access to Rules, allowing them to view rule details and audit logs while being restricted from editing rules. • Validation that users with the MMD Template Management Stream security group, with or without additional security group memberships, can view Templates and Clauses and successfully download the Word version. • Validation that Edit and Terminate actions are not available for Templates and Clauses for users under the new MMD Template Management Stream security group, regardless of additional security group combinations. |  |  |  | [4/7] Waiting for confirmation regarding the US [4/15] tagged as on hold for now since need the discussion with Legal.
Guna | Jonathan | 16 | 1053554 | TPRM | [TPRM Initiative][Functional][Part 1] Update attribute labels and its values in MMD | Completed Execution Review | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1053554 | Type: SREQ, SMA, SCC, SSW, BSR and SynOps • Validation of the Updated attribute labels and its values in MMD under Risk and compliance section - Supplier provision of PII back, Supplier AI PII Processing Future, DOJ Types of Bulk Sensitive Data and DOJ Prohibited Countries. • Validation of removing the attributes in MMD - Supplier PII Subjects Numbers, Supplier provision of PII back Type and Accenture sharing as controller All validations and rules update will be tested with the following - Direct Creation of SREQ request - Direct Creation of Agreements (SMA, SCC, SSW) - Creation from SREQ request to Agreement until Executed status - Creation of SynOps request to SCC agreement until Executed status - Creation of BSR request to SMA agreement until Executed status | Type: SREQ / SMA • Inflight - Check for existing attribute labels and values in MMD under Risk and compliance section
Guna | Izzy | 16 | 1073960 | TPRM | [TPRM Initiative][Technical][Part 1]Update attribute mapping from Coupa to MMD system | Completed Execution Review | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1077051 | Coupa ---> MMD Type: SREQ, SMA, SCC, SSW • Validation of attribute lables and values which is integrated using Coupa ID - DOJ Types of Bulk Sensitive Data and DOJ Prohibited Countries • Validation of removed attributes from MMD which is integrated between Coupa and MMD - Supplier PII Subjects Numbers, Supplier provision of PII back Type and Accenture sharing as controller All validations and rules update will be tested with the following, - Direct Creation of SREQ request - Direct Creation of Agreements (SMA, SCC, SSW) - Creation from SREQ request to Agreement until Executed status | Type: SREQ / SMA • Inflight - Validate the existing attributes in MMD under Risk and compliance section using Coupa ID • Validation of attributes integrated between Coupa and MMD before removal - Supplier PII Subjects Numbers, Supplier provision of PII back Type and Accenture sharing as controller
Izzy | El/Jhea/Guna/Tine | 16 | 1054356 | KTLO | Supplier Preferred Name Values Translation to French, Spanish, Italian, German and Portuguese | Completed Execution Review | TC-MMD_BuySide_R26.3_S16_1054356_Supplier Preferred Name Values Translation to French, Spanish, Italian, German and Portuguese | Type: SMA, SSW, SCC • Validation of the additional dropdown options for Supplier Preferred Name should be selectable. Additional dropdown options: Agency Authorized Distributor Buyer Contracting Party Contractor Customer Distributor Independent Contractor Licensee Licensor Managed Service Provider (MSP) Manufacturer Merchant Producer Publisher Retailer Seller Service Provider Staffing Agency Subcontractor Systems Integrator Temp Agency Wholesaler • Validation of Language for: French, Spanish, Italian, German and Portuguese • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause. |  |  | Type: SMA, SSW, SCC • Validation of the additional dropdown options for Supplier Preferred Name should be selectable. Additional dropdown options: Agent Artist Consultant Expert License Provider Supplier Vendor • Validation of Language for: French, Spanish, Italian, German and Portuguese • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause. | On Hold - Translation-related user story not reflecting in QA despite completed configuration; under investigation with release and technical teams. [4/28] Included in S17 P2P
Jonathan | Elealeh | 17 | 1080462 | KTLO | Create Read-only role for Rules, clauses and templates in QA, Prodfix, Prod | Completed Execution Review | Test Case 1080461: 1.1 SREQ, SMA, SCC, SSW Validation of the new security group MMD Template Clauses and Rules Stream | • Validation that users assigned to the new security group have view‑only access to rules, allowing them to view rule details and audit logs without the ability to edit the rules. • Validation that users in the new security group can download the Word version of templates and clauses. • Validation that users in the new security group are restricted from editing or terminating templates and clauses. • Validation that users assigned to the new MMD Template Management Stream security group, either alone or in combination with Procurement, Legal, Business, Enhanced Business, Delegated Spend, or Buyside Leadership security groups, have view‑only access to Rules, allowing them to view rule details and audit logs while being restricted from editing rules and should retain their original access and If new Security Group are added to other accesses this should elevate their access with the purpose of having the view of the Rules, and View and download templates and clauses • Validation that users with the MMD Template Management Stream security group, with or without additional security group memberships, can view Templates and Clauses and successfully download the Word version. • Validation that Edit and Terminate actions are not available for Templates and Clauses for users under the new MMD Template Management Stream security group, regardless of additional security group combinations. | • Validation of Dashboard Tiles Visibility in Security Groups (Legal, Procurement, Business, Enhance Business, Buyside Leadership, Delegated Spend) before combination of access with the new security group MMD Template Clauses and Rules Stream and after combination. • Validation of the original dashboard tile visibility of the Said security groups. | • Vallidation of removal of new security group which combined the other security group (Legal, and Procurement) which untriggers the acces given by the new security group of accessing the rules and viewing them, and can download the version template in cluases and templates.
Izzy | Astha/Jhea | 17 | 1071312 | KTLO | Supplier Preferred Name Values Translation to Chinese | Completed Execution Review | TC-MMD_BuySide_R26.3_S17_1071312_Supplier Preferred Name Values Translation to Chinese | Type: SMA, SSW, SCC • Validation of the additional dropdown options for Supplier Preferred Name should be selectable. Additional dropdown options: Advisor Agency Agent Artist Authorized Distributor BDA Beneficiary Buyer Consultant Contracting Party Contractor Customer Distributor Expert Grantee Independent Contractor Lessor License Licensee Licensor Luminary Managed Service Provider (MSP) Manufacturer Merchant Partner Producer Production House Provider Publisher Purchaser Retailer Seller Service Provider Speaker Sponsor Staffing Agency Subcontractor Supplier Systems Integrator Temp Agency Vendor Wholesaler • Validation of Language for: Chinese • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause (Split View) |  | Type: SMA, SSW, SCC • Validation of the Supplier Preferred Name from default during the agreement's ‘In Progress’ state. • Validation of changing the language from Chinese to another language. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause (Split View).
Jhea | Izzy | 17 | 1073086 | KTLO | FY26 Collateral - Iberia Market Unit rename | Completed Execution Review | TC-MMD_BuySide_R26.3_S17_1073086 FY26 Collateral - Iberia Market Unit rename | Type: Request, SMA, SCC, SSW • Validation of when selecting country Andorra, Portugal and Spain, Market Unit is SPP • Validation of expected attribute values during "Assigned/In Progress" status. • Validation of added user in the team tab: MMD.Buy.Proc.SPP.RegionalCoordinator Client Deal Internal Project or Client Offering -Internal Project Where do you intend to use the product/service? -Single Market Unit, multiple countries | Type: Request, SMA, SCC, SSW • Validation of Market Unit and Client Group (CG) updated values of country Andorra, Portugal and Spain in the Inflight request/agreement. Client Deal Internal Project or Client Offering -Single Client Deal Subcontractor or Supplier Do you have the Opportunity ID for this client matter? -Yes Enter the MMS Opportunity ID and press "Validate" to populate this form -0011267801 | Type: Request • Validation of expected updated attribute value during "Assigned" status. • Validate user must not be added in the team tab: MMD.Buy.Proc.SPP.RegionalCoordinator
Arianne | Astha/Izzy | 17 | 1082312 | KTLO | Signed contracts should retain supplier preferred name translation | Business Reviewed | TC-MMD_BuySide_R26.3_S17_1082312_Signed ontracts should retain supplier preferred name translation | Type: Request, SMA, SCC, SSW • Validation of the original translation of the following values for Supplier Preferred Name under Business Status: Executed, Expired, Teminated, Termination Pending - Advisor - BDA - Beneficiary - Grantee - Lessor - Luminary - Partner - Production House - Purchaser - Speaker - Sponsor Languages: French, Spanish, Italian, German, Portuguese and Chinese • Validation of the updated translation of the values mentioned above for Supplier Preferred Name for the newly created contracts • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause (Split View) |  | Type: Request, SMA, SCC, SSW • Validation of the updated translation of the following values for Supplier Preferred Name under Businees Status: Executed, Expired, Teminated, Termination Pending - Advisor - BDA - Beneficiary - Grantee - Lessor - Luminary - Partner - Production House - Purchaser - Speaker - Sponsor Languages: French, Spanish, Italian, German, Portuguese and Chinese • Validation of changing the language from the old values to updated values • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause (Split View).
Guna | Arianne | 17 | 1081979 | TPRM | [TPRM Initiative][Functional][Part 2] Update attribute labels and its values in MMD | Completed Execution Review | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1081979/ | Type: SREQ, SMA, SCC, SSW, BSR and SynOps • Validation of newly created attributes in MMD - Supplier Access to Data New and Supplier PII Cross-border transfer New • Validation of the Updated attribute labels and its values in MMD under Risk and compliance section - Supplier provision of PII back, Supplier PII Subjects, Supplier Types of PII, Accenture processing as controller Types, Accenture Adequate Countries Transfer and Supplier PII types of origin. • Validation of removing the attributes in MMD - Supplier Access to Data, Supplier Access to PII, Supplier PII Cross-border transfer and Supplier AI PII Processing All validations and rules update will be tested with the following - Creation from SREQ request to Agreement until Executed status - Creation of SynOps request to SCC agreement until Executed status - Creation of BSR request to SMA agreement until Executed status | Type: SREQ / SMA • Inflight - Check for existing attribute labels and values in MMD under Risk and compliance section
Guna | Jonathan | 17 | 1081986 | TPRM | [TPRM Initiative][Technical][Part 2]Update attribute mapping from Coupa to MMD system | Business Reviewed | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1081986/ | Coupa ---> MMD Type: SREQ, SMA, SCC, SSW, BSR and SynOps • Validation of attribute lables and values which is integrated using Coupa ID - Supplier provision of PII back, Supplier PII Subjects, Supplier Types of PII, Accenture processing as controller Types, Accenture Adequate Countries Transfer and Supplier PII types of origin. • Validation of removed attributes from MMD which is integrated between Coupa and MMD - Supplier Access to Data, Supplier Access to PII, Supplier PII Cross-border transfer and Supplier AI PII Processing • Validation of newly created attributes in MMD using Coupa ID - Supplier Access to Data New and Supplier PII Cross-border transfer New All validations and rules update will be tested with the following, - Creation from SREQ request to Agreement until Executed status - Creation of SynOps request to SCC agreement until Executed status - Creation of BSR request to SMA agreement until Executed status | Type: SREQ / SMA • Inflight - Validate the existing attributes in MMD under Risk and compliance section using Coupa ID • Validation of attributes integrated between Coupa and MMD before removal - Supplier Access to Data, Supplier Access to PII, Supplier PII Cross-border transfer and Supplier AI PII Processing
Jhea | Izzy | 18 | 1069754 | KTLO | [Collateral] - Management Hierarchy Client Group Iberia rename | Business Reviewed | User Story 1069754 [Collateral] - Management Hierarchy Client Group Iberia rename | Type: SREQ, SMA, SCC, SSW • Validation of when selecting Andorra/Portugal/Spain and entering Opportunity ID, Client Group is automatically set to either of the values (SPP CMT, SPP FS, SPP H&PS, SPP PRD, or SPP RES) • Validated the expected attribute values during in "Assigned/In Progress" status. Client Deal Internal Project or Client Offering -Single Client Deal Subcontractor or Supplier Do you have the Opportunity ID for this client matter? -Yes Enter the MMS Opportunity ID and press "Validate" to populate this form -0011267801 | Type: SREQ, SMA, SCC, SSW • Validation of created Inflight request/agreement is correctly updated with the expected client group values. (SPP CMT, SPP FS, SPP H&PS, SPP PRD, or SPP RES) • Validation of expected attribute values during in "Assigned/In Progress" status.
Jonathan | Astha | 18 | 1089866 | KTLO | Adding users in the new security group MMD Templates Clauses and Rules Stream Group | Business Reviewed | Test Case 1105899: Validation of adding Users to MMD Templates Clauses and Rules Stream Security Group Test Case 1105937: Inflight Validation of adding Users to MMD Templates Clauses and Rules Stream Security Group | • Validation that users Prasad Shweta, Pandey Pooja, and Shankar Sushma is added in the new security group MMD Templates Clauses and Rules Stream Group in users dropdown in the admin tile and security groups tab. | • Validation of Before and After scenario of users Prasad Shweta, Pandey Pooja, and Shankar Sushma is not added in the new security group MMD Templates Clauses and Rules Stream Group before deployment and to be added in after deployment on MMD Templates Clauses and Rules Stream Group in users dropdown in the admin tile and security groups tab.
Izzy | El/Jhea | 18 | 1097492 | KTLO | Supplier Preferred Name Values Translation to Japanese | Business Reviewed | TC-MMD_BuySide_R26.3_S18_1097492_Supplier Preferred Name Values Translation to Japansese | Type: SMA, SSW, SCC • Validation of the additional dropdown options for Supplier Preferred Name should be selectable. Additional dropdown options: Advisor Agency Agent Artist Authorized Distributor BDA Beneficiary Buyer Consultant Contracting Party Contractor Customer Distributor Expert Grantee Independent Contractor Lessor License Licensee Licensor Luminary Managed Service Provider (MSP) Manufacturer Merchant Partner Producer Production House Provider Publisher Purchaser Retailer Seller Service Provider Speaker Sponsor Staffing Agency Subcontractor Supplier Systems Integrator Temp Agency Vendor Wholesaler • Validation of Language for: Japanese • Validation of the selected value showing in the summary details page. • Validation of the Supplier Preferred Name by changing the Language Preference settings and is correctly inherited and displayed in the Template and Clause |  | Type: SMA, SSW, SCC • Validation of the Supplier Preferred Name from default during the agreement's ‘In Progress’ state. • Validation of changing the language from Japanese to another language. • Validation of the Supplier Preferred Name is correctly inherited and displayed in the Template and Clause
Elealeh | Jhoanna | 18 | 1093921 | KTLO | Enhance GLN Triage Requirements Routing Rules | Business Reviewed | TC-MMD_BuySide_R26.3_S18_1093921 Enhance GLN Triage Requirements Routing Rules.xlsx | Type: SREQ, BSR to SREQ Client Deal - Single Client Offering (6) Countries: Morocco, France, PH, Canada, Puerto Rico, Japan Validation of the following Rules: - GLN Request Routing: Rule #2, #4, #5, #6 All validations and rules update will be tested with the following - With or Without Opportunity Id - Direct Creation of Request - BSR to MMD Request |  | Type: SREQ Client Deal - Single Client Offering (9) Countries: USA, Morocco Validation of the following Rules: - Not contains GLN Request Routing: Rule #2, #4, All validations and rules update will be tested with the following - Opportunity Id has and no values. - Direct Creation of Request - BSR to MMD Request
Elealeh/Jhoanna | Jhoanna/El/Jonathan/Jhea | 18 | 1093963 | KTLO | Technical Configuration – Review Functionality for Single Client Deal | Business Reviewed | TC_MMD_Buyside_R26.3_S18_1093963_Technical Configuration – Review Functionality for Single Client Deal.xlsx | Type SMA, SCC, SSW Legal Request Review Behavior ⦁ Validate the Single Client Deal process using GLN countries and Request Review Rules. ⦁ Validate the Legal Request Review functionality and the “Request Review” button behavior. ⦁ Validate that once the “Request Review” button is triggered/clicked, the status changes to “Request Review in Progress” for the GLN user group. ⦁ Validate the users assigned under the GLN user group. Cancellation ⦁ Validate that the Primary Owner can cancel a request review that is in “Request Review in Progress” status, and confirm that the “Validate for Signature” button becomes visible again. ⦁ Validate the following upon cancellation: ⦁ If the agreement is rejected/approved, the request should be removed from the task list of users belonging to the GLN group. ⦁ The “Validate for Signature” button should become visible again. ⦁ The contract should proceed to the next phase without requiring legal review, while still allowing the option to request GLN Legal review again. ⦁ Validate that users other than the Primary Owner are not allowed to cancel the review request. Delegation ⦁ Validate adding a delegated user through Preferences and ensure support for parallel legal reviews based on configuration. ⦁ Validate that the system supports sequential legal reviews based on configuration. ⦁ Validate that reviewer delegation follows the existing delegation rules. Additional Validations ⦁ Direct creation from SMA, SCC, and SSW. ⦁ Validation up to Executed status. ⦁ Validation of Request functionality for SMA, SCC, and SSW. |  | Type: SMA, SCC, SSW - If Signature Type = Fully Signed, the system should skip GLN review and move the agreement directly to Executed. - This scenario validates that GLN review is NOT triggered. Any occurrence of GLN review steps, related UI actions, or incorrect status (e.g., In Progress) indicates a failure.
Guna | Izzy | 18 | 1101229 | TPRM | [TPRM Initiative] Make Supplier AI PII Processing attribute visible in MMD UI | Business Reviewed | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1101229 | Type: SREQ, SMA, SCC, SSW, BSR and SynOps • Validating the visiblity of removed attribute in MMD - Supplier AI PII Processing All validations and rules update will be tested with the following - Creation from SREQ request to Agreement until Executed status - Creation of SynOps request to SCC agreement until Executed status - Creation of BSR request to SMA agreement until Executed status | Type: SREQ / SMA • Inflight - Validate if Supplier AI PII Processing attribute label and values is not present in MMD under Risk and compliance section
Jonathan | Astha | 18 | 1088601 | KTLO | Display error Pop-up if SOW Effective Date exceeds End Date for SSW and SCC | Business Reviewed | Test Case 1111032: 1.1 Validation of Display error pop-up when Contract Change Effective Date exceeds End Date on SCC Test Case 1111138: 1.2 Validation of Display error pop-up when SOW/Order Effective Date exceeds End Date on SSW Test Case 1111243: 1.3 Validation of Inflight Scenario Display error pop-up when Contract Change Effective Date exceeds End Date on SCC Test Case 1111314: 1.4 Validation of Inflight Scenario Display error pop-up when SOW/Order Effective Date exceeds End Date on SSW Test Case 1111384: 1.5 Validation of Negative Scenarios Display error pop-up when SOW/Order Effective Date and Contract Change Effective Date exceeds End Date on SSW and SCC | Type: SCC, SSW • Using procurement access validation of Effective date having a date that exceeds the end date. • Validation of Effective date having a date that exceeds the end date and a pop-up error message will appear and preventing in creating the agreement. • Validation of closing the pop-up error message will redirect to the attribute that has error message. • Validation of Effective date having a date of before or equal to the end date and a pop-up error message will not appear and creating agreement is successful. - Creation of direct SCC and SSW (Validating in different statuses "In Progress", "Ready for signature", "Executed" business statuses. | Type: SCC, SSW Before Deployment: • Using procurement access validation of Effective date having a date that exceeds the end date. • Validation of Effective date having a date that exceeds the end date and a pop-up error message will not appear and creating the agreement successfully. After Deployment: • Using procurement access validation of Effective date having a date that exceeds the end date. • Validation of Effective date having a date that exceeds the end date and a pop-up error message will appear and preventing in creating the agreement. • Validation of closing the pop-up error message will redirect to the attribute that has error message. • Validation of Effective date having a date of before or equal to the end date and a pop-up error message will not appear and creating agreement is successful. - Creation of direct SCC and SSW (Validating in different statuses "In Progress", "Ready for signature", "Executed" business statuses. | Type: SCC, SSW • Using of (Buyside Leadership, Legal, Delegated Spend) access validation of Effective date having a date that exceeds the end date and a pop-up error message will not appear and successfully agreement. - Creation of direct SCC and SSW (Validating in phase "In Progress" business status.
Arianne |  | 18 | 1093873 | KTLO | Require MMS Opportunity ID on Agreement Creation for Single Client Deals | Not Applicable | TC_MMD_BuySide_R26.3_S18_1093873_MMS Opportunity ID on Agreement Creation for Single Client Deals.xlsx | Type: SMA, SCC and SSW Validation of the following: - Agreement must not be created when MMS Opportunity ID is blank - Agreement must not be created when MMS Opportunity ID is invalid/incorrect - Corresponding attributes must be inherited by the populated MMS Opportunity ID |  | Type: SMA, SCC and SSW Validation of the following: - Agreement must be created when the attribute: Do you have the Opportunity ID for this client matter? Is populated to "No" |  | [5/14] FA Review: No need for testing
Guna |  | 18 | 1099787 | TPRM | Disable DOJ notification triggers in MMD Production | Not Applicable | [5 empty] | Story is removed and not part of S18
Guna |  | 19 | 1099816 | TPRM | [TPRM Initiative] Translation of Attributes under Risk and compliance section | Not Applicable | [5 empty] | Hema Confirmed - Haven't yet recieved the translation file from Ligia Rolled over to S19
Guna |  | 20 | 1131246 | TPRM | [TPRM Initiative][Functional][Part 3] Update attribute labels and its values in MMD | For Test Lead/Sprint Lead/FA Review | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1131246 | Type: SREQ, SMA, SCC, SSW and BSR • Validation of newly created attributes in MMD - Supplier provision of PII back New • Validation of Rules for replacement of attributes All validations and rules update will be tested with the following - Creation from SREQ request to Agreement until Executed status - Creation of BSR request to SMA agreement until Executed status | Type: SREQ / SMA • Inflight - Check for existing attribute label and values in MMD under Risk and compliance section - Supplier provision of PII back
Guna |  | 20 | 1131306 | TPRM | [TPRM Initiative][Technical][Part 3] Update attribute labels and its values in MMD | For Test Lead/Sprint Lead/FA Review | https://dev.azure.com/accenturecio24/CategoryToContract_PR1085/_workitems/edit/1131306 | Coupa ---> MMD Type: SREQ, SMA, SCC, SSW, BSR and SynOps • Validation of newly created attributes in MMD integrated using Coupa ID - Supplier provision of PII back New All validations and rules update will be tested with the following, - Creation from SREQ request to Agreement until Executed status - Creation of BSR request to SMA agreement until Executed status |  |  |  | For September Release
Note on J10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Tan, Elealeh bini create you ng inflight na direct creation lang ng 1 request and 1 bsr to request na may added na contract admin.
Note on F11: Jagadeeswaran, Guna Raja Jayashree: On Hold - Need a discussion with Legal

## Report
KTLO/TPRM Sprint 15
User Stories | Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assigned Tester | Comment
TC-MMD_BuySide_R26.3_S15_1041077_[KTLO] [MMD BuySide][R26.2 QA, PRDFIX] - Excess signatory is showing in the signatory field | 8 | 0 | 0 | 0 | 0 | 8 |  | Guna
TC-MMD_BuySide_R26.3_S15_1044636_[KTLO]_[Buy Side R26.2 S14] - Supplier Permitted Termination Date is not updating in Save Search in agreement list | 10 | 0 | 0 | 0 | 0 | 10 |  | Arianne
TC-MMD BuySide R26.3 S15 858074 [KTLO] [CHG] [FEEDBACK] Additional Dropdown option for Supplier Preferred Name.xlsx | 129 | 0 | 0 | 0 | 0 | 129 |  | El,Astha,Izzy
TC-MMD_BuySide_R26.3_S15_1053552 [TPRM] [Functional] Unhide Unknown option in DOJ prohibited countries attribute in MMD.xlsx | 9 | 0 | 0 | 0 | 0 | 9 |  | Jhea
TC-MMD_BuySide_R26.3_S15_1053553 [TPRM][Technical] Update Coupa mapping for Unknown option in DOJ prohibited countries attribute in MMD.xlsx | 7 | 0 | 0 | 0 | 0 | 7 |  | Jonathan
TC-MMD_BuySide_R26.3_S15_611512_[KTLO_BuySide]_Edit in Office for the Web when status is Ready For Signature | 3 | 0 | 0 | 0 | 0 | 3 |  | Arianne
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA
| 166 | 0 | 0 | 0 | 0 | 166 | 0
KTLO/TPRM Sprint 16
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assigned Tester | Comment
Bug 1061641: [MMD BuySide][R26.3] Attribute Value discrepancy for "Is Contract Admin Present" for business status Assigned or Assignment Pending is displayed in Saved Search | 10 | 0 | 0 | 0 | 0 | 10 | 0 | Arianne
User Story 1053554 [TPRM Initiative][Functional][Part 1] Update attribute labels and its values in MMD | 10 | 0 | 0 | 0 | 0 | 10 | 0 | Jonathan
User Story 1073960 [TPRM Initiative][Technical][Part 1]Update attribute mapping from Coupa to MMD system | 9 | 0 | 0 | 0 | 0 | 9 | 0 | Izzy
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA
| 29 | 0 | 0 | 0 | 0 | 29 | 0
KTLO/TPRM Sprint 17
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assignee
Create Read-only role for Rules, clauses and templates in QA, Prodfix, Prod | 16 | 0 | 0 | 0 | 0 | 16 |  | El
Supplier Preferred Name Values Translation to Chinese | 129 | 0 | 0 | 0 | 0 | 129 |  | Astha/Jhea
FY26 Collateral - Iberia Market Unit rename | 21 | 0 | 0 | 0 | 0 | 21 |  | Izzy
[TPRM Initiative][Functional][Part 2] Update attribute labels and its values in MMD | 5 | 0 | 0 | 0 | 1 | 6 |  | Tin/Guna
Supplier Preferred Name Values Translation to French, Spanish, Italian, German and Portuguese | 438 | 0 | 0 | 0 | 0 | 438 |  | El/Jhea/Guna/Tine | Sprint 16 US but Included in S17 P2P
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA
| 609 | 0 | 0 | 0 | 1 | 610 | 0
KTLO/TPRM Sprint 18
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Total - NA | Assignee
[Collateral] - Management Hierarchy Client Group Iberia rename | 8 | 0 | 0 | 0 | 0 | 8 |  | Izzy
Adding users in the new security group MMD Templates Clauses and Rules Stream Group | 2 | 0 | 0 | 0 | 0 | 2 |  | Astha
Supplier Preferred Name Values Translation to Japanese | 129 | 0 | 0 | 0 | 0 | 129 |  | El/Jhea
Enhance GLN Triage Requirements Routing Rules | 5 | 0 | 0 | 0 | 0 | 5 |  | Jhoanna
Technical Configuration – Review Functionality for Single Client Deal | 46 | 0 | 0 | 0 | 0 | 46 |  | Jhoanna/El/Jonathan/Jhea
[TPRM Initiative] Make Supplier AI PII Processing attribute visible in MMD UI | 6 | 0 | 0 | 0 | 0 | 6 |  | Izzy
Display error Pop -up if SOW Effective Date exceeds End Date for SSW and SCC | 4 | 0 | 0 | 0 | 0 | 4 |  | Astha
Require MMS Opportunity ID on Agreement Creation for Single Client Deals | 0 | 0 | 0 | 0 | 0 | 0
Disable DOJ notification triggers in MMD Production | 0 | 0 | 0 | 0 | 0 | 0
[TPRM Initiative] Translation of Attributes under Risk and compliance section | 0 | 0 | 0 | 0 | 0 | 0
[TPRM Initiative][Functional][Part 3] Update attribute labels and its values in MMD | 6 | 0 | 0 | 0 | 0 | 6 |  | Guna
[TPRM Initiative][Technical][Part 3] Update attribute labels and its values in MMD | 4 | 0 | 0 | 0 | 0 | 4 |  | Guna
[TPRM Initiative][Technical][Part 2]Update attribute mapping from Coupa to MMD system | 4 | 0 | 0 | 0 | 0 | 6 |  | Jonathan
Signed contracts should retain supplier preferred name translation | 76 | 0 | 0 | 0 | 0 | 76 |  | Astha/Izzy
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Total - NA
| 290 | 0 | 0 | 0 | 0 | 292 | 0
8.7.4.45 Hotfix Regression
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assignee
MMD to SCC_Contract TC Rules Update - Legal Rules | 2 | 0 | 0 | 0 | 0 | 0 | 0
BSR to MMD_SCC_ Rules to set values to Data Privacy Schedules | 2 | 0 | 0 | 0 | 0 | 23 | 23
MMD to SSW_Update on the Request Review functionality of "Any" instead of "All" and Technical Configuration Logic | 2 | 0 | 0 | 0 | 0 | 7 | 7
MMD to SMA_Market Unit Buy and Market Buy Changes for Growth Markets and Europe | 2 | 0 | 0 | 0 | 0 | 18 | 18
MMD to SMA_TPRM to MMD Integration | 0 | 0 | 0 | 0 | 2 | 0 | -2
MMD SSSR to FIND_Serbia | 2 | 0 | 0 | 0 | 0 | 23 | 23
SUB_SBS_Germany | 2 | 0 | 0 | 0 | 0 | 7 | 7
| 2 | 0 | 0 | 0 | 0 | 18 | 18
| Passed | Failed | In Progress | Not Started | Not Applicable | Total
| 14 | 0 | 0 | 0 | 2 | 96 | 94
June Release 26.3 Mock Test
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assignee | Comment
Scenario 1 - SREQ to SMA_USA | 25 | 2 | 0 | 0 | 0 | 27 |  | Izzy | SREQ GLN & Bug 1129749: [Buy Side - R26.3] Purchase Category is not match both QA and Prodfix | [6/1] Rethanya: We are moving the master data again through p2p for purchase category on 4th June p2p. we will keep you posted once its ready for testing in prdfix. [6/2] We encountered some issues, but since it's not a blocker, we can proceed with sign-off. We'll re-test Scenario 1 once the issue is fixed.
Scenario 2- SREQ to SCC_France | 41 | 0 | 0 | 0 | 0 | 41 |  | Jhea
Scenario 3: SREQ to SSW_Portugal | 50 | 3 | 0 | 0 | 0 | 53 |  | Astha | SREQ GLN & Bug 1129749: [Buy Side - R26.3] Purchase Category is not match both QA and Prodfix | [6/1] Rethanya: We are moving the master data again through p2p for purchase category on 4th June p2p. we will keep you posted once its ready for testing in prdfix. [6/2] We encountered some issues, but since it's not a blocker, we can proceed with sign-off. We'll re-test Scenario 1 once the issue is fixed. It will be retested in smoke testing for june release.
Scenario 4: SSSR to FIND_Strategic Partner_ Germany | 6 | 0 | 0 | 0 | 0 | 6 |  | Jho
Scenario 5: BSR to SMA_PH | 24 | 0 | 0 | 0 | 0 | 24 |  | Ele
Scenario 6: SYNOPS to SCC_Spain | 0 | 0 | 0 | 0 | 28 | 0 |  | Guna | Integration is failed from Synops to MMD because of newly created attributes as part of TPRM US and that changes should be implemented in SynOps aswell - Supplier Access to Data New attribute
Scenario 7: MMD Templates, Clauses & Rules – Read-Only Security Group Validation (Admin Access Only) (Mock & Smoke) | 13 | 0 | 0 | 0 | 0 | 13 |  | Jonathan
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA
| 159 | 5 | 0 | 0 | 28 | 164 | 0
June Release 26.3 Smoke Test
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA | Assignee | Comment
Scenario 1 - SREQ to SMA_USA |  |  |  | 27 |  | 27 |  | Tin
Scenario 2- SREQ to SCC_France |  |  |  | 38 |  | 38 |  | Arianne
Scenario 3: SREQ to SSW_Portugal |  |  |  | 50 |  | 50 |  | Arianne
Scenario 4: SSSR to FIND_Strategic Partner_ Germany |  |  |  | 6 |  | 6 |  | Hema
Scenario 5: BSR to SMA_PH |  |  |  | 26 |  | 26 |  | Tin
Scenario 6: SYNOPS to SCC_Spain |  |  |  | 28 |  | 28 |  | Guna
Scenario 7: MMD Templates, Clauses & Rules – Read-Only Security Group Validation (Admin Access Only) (Mock & Smoke) |  |  |  | 13 |  | 13 |  | Sheena
Scenario 8: Direct SMA Creation |  |  |  | 9 |  | 9 |  | Guna
| Passed | Failed | In Progress | Not Started | Not Applicable | Total | Tota - NA
| 0 | 0 | 0 | 197 | 0 | 197 | 0

## BUG
Sprint Bugs
Area | Bug ID | SPRINT | Summary | Status | Severity | Found In | Country | Impacted | Opened | Comment
KTLO | 1131593 | 20 | [Buy Side - R26.3] [SCC Agreement] Missing Recipient Name in “For Your Review” Email Notification | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | 2026-06-01
KTLO | 1131694 | 20 | [Buy Side - R26.3] [OTP Screen] Countdown Timer Placeholder ({0}:{1}) Displayed Instead of Actual Time | Active | 3 - Medium | QA | Global | SMA,SCC,SSW | 2026-06-01 | For Retest
KTLO | 1108153 | 18 | [MMD Buy Side - R26.3 QA] - Coupa ID values are not integrating upon triggering of the Coupa ID. | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-12
KTLO | 1131503 | 20 | [Buy Side - R26.3] Error while retrieving data from MMS when validating Opportunity ID on Create Contract Request | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | 2026-06-01
KTLO | 1129174 | 19 | [Buy Side - Release QA] Required Association for Supplier Order or SOW | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-25
KTLO | 1128512 | 19 | [Buy Side - 26.3] Category Group dropdown does not load on initial click of “Get Categories” button | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-24
KTLO | 1119900 | 19 | [Buy FY26.3] [QA] Attribute label is displayed incorrectly in category attributes (shows technical field name) | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-20
TPRM | 1117652 | 19 | Supplier PII Cross-Border Transfer New attribute dropdown displays 2 extra Countries | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-19
KTLO | 1118820 | 18 | [Buy Side - 26.3] Agreements not getting expired even though end date is passed | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-20
KTLO | 1110287 | 18 | [Buy Side - R26.3] Supplier Preferred Name values “Advisor” and “Agent” are not translated to Chinese(Simplified) across all agreement types: SMA, SCC, and SSW. | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-12
KTLO | 1100995 | 18 | [MMD Buy Side R26.3 S18] - Unable to get supplier details | Closed - Verified | 3 - Medium | QA | Global | SMA,SCC,SSW | May-5
Mock Testing Bugs
Area | Bug ID | SPRINT | Summary | Status | Severity | Found In | Country | Impacted | Opened | Comment
KTLO | 1129749 | 19 | [Buy Side - R26.3] Purchase Category is not match both QA and Prodfix | Closed - Verified | 3 - Medium | Prodfix and QA | Global | SREQ, SMA,SCC,SSW | May-29 | [6/1] Rethanya: We are moving the master data again through p2p for purchase category on 4th June p2p. we will keep you posted once its ready for testing in prdfix.
KTLO | 1129099 | 19 | [Buy Side - R26.3][Prdfix] Closing the pop-up error message the screen does not focus to date entry field which has an error | Closed - Verified | 3 - Medium | Prodfix | Global | SMA,SCC,SSW | May-28
KTLO | 1128869 | 19 | [Buy Side - R26.3 Prodfix] – Section 02 only appears after double refresh in FIND | Rejected | 3 - Medium | Prodfix | Global | SMA,SCC,SSW | May-28
KTLO | 1129200 | 19 | [Buy Side - R26.3] [Prdfix] Approvers Removed in Teams Tabs Still Visible in Assignment Pending | Rejected | 3 - Medium | Prodfix | Global | SMA,SCC,SSW | May-28

## Regression
Scope | Passed | Failed | In Progress | Not Started | Not Applicable | Total
Default rules and Logic | 1 | 0 | 9 | 6 | 0 | 16
Reviewer/Approver Functionality | 0 | 0 | 3 | 0 | 0 | 3
Restriction of Contracts/restricted country | 2 | 0 | 1 | 0 | 0 | 3
Integrations supplier | 2 | 0 | 0 | 1 | 2 | 5
Auto Provissioning | 0 | 0 | 0 | 1 | 1 | 2
Email Notification | 0 | 0 | 0 | 2 | 0 | 2
Peer to Peer | 1 | 0 | 2 | 3 | 0 | 6
| Passed | Failed | In Progress | Not Started | Not Applicable | Total
| 6 | 0 | 15 | 13 | 3 | 37

## Smoke Test
Smoke Testers
Team | Name | Email Address | Contact Number | Has Prod Access | User Access (Roles) | Need Prod Access? | Available | Need Email Override | [5 empty] | Task Name | Total Duration | CDT Start | CDT Finish | IST Start | IST Finish | Phil Start date | Phil End date | ARG start time | ARG end time
MMD FA/BA | Barcillano, Sheena | sheena.m.barcillano@accenture.com | 9155584623 |  | Admin | Yes |  | -
| Priya, Hema | hema.priya.r@accenture.com |  | Yes | Admin | Yes | Yes | - | [5 empty] | Buy Side - Accenture Write Test/Smoke test/BSR to MMD Integration | 3 hrs | Sat 6/13/26 2:45 PM | Sat 6/13/26 5:45 PM | Sun 6/14/26 1:15 AM | Sun 6/14/26 4:15 AM | Sun 6/14/26 3:45 AM | Sun 6/14/26 6:45 AM | Sat 6/13/26 4:45 PM | Sat 6/13/26 7:45 PM
MMD Buy Side Testing Team | Aban, Ma. Cristine | ma.cristine.s.aban@accenture.com | 639451369473 | Yes | Admin | Yes | Yes | - |  | Test Lead tasks:
| Arianne M. Abuque | arianne.c.abuque@accenture.com | 9770363630 | Yes | Legal, Procurement | Yes | Yes | - |  | Contact the Testing team/BSR
| Jerome Narvacan | jerome.narvacan@accenture.com | 639276860889 | No | Procurement | Yes | Yes | - |  | Confirm from Diego when testing team have action item on the 1st BSR activities since we have 2 activities for BSR
| Jagadeeswaran, Guna | guna.r.jagadeeswaran@accenture.com | 639155242994 | Yes | Procurement | Yes | Yes | -
BSR | Alibarbar, Diether | diether.j.alibarbar@accenture.com | 639394679695 |  |  |  |  | - |  | -setup messenger group with Jof, Sheena, Cut, Dev team, BSR Team
| Rosales, Margarett | margarett.rosales@accenture.com | 9954842174 |  |  |  |  | - |  | Collaborate with Diego, during his time so we can be aligned
SYNOPS | Shiva, Krishna | shiva.v.krishna@accenture.com
TPRM | Agkis, Hennessey Croizette | hennessey.c.o.agkis@accenture.com | 9182968034
| Sarigumba, Charina | charina.sarigumba@accenture.com
| Duration | PH Start | PH Finish | [6 empty] | -once identified on the date & time, if timing falls PH time we need to cover Diego on the meetings
| 3 hrs | [8 empty] | Create Teams GC with PH Testing team and BSR
Task Name | [9 empty] | Once BSR activities starts, text message the BSR team as some are not online in Teams
Buy Side - Accenture Write Test/Smoke test/BSR to MMD Integration | 3 hrs |  |  | Jonathan Carpio | [5 empty] | Contact the team in Messenger GC
Check the meeting timing and/or we are on-track on the activities
During the call with Cut, for final touchpoint Test Lead needs to join and say the testing status (if no issues or other)
Smoke Test File: | 26.3 June Release - Smoke Testing | [8 empty] | Sending of Overall Testing results via email including the BSR test result
*Note: Update the Agreement/SREQ title, must contain "CIO-TEST".
Status email to be provided with green highlight
[10 empty] | Date/Time (ARG) | To send email | Subject | Invitation | MMD TEAM | Invitation | Notes
[10 empty] | Dec 13, 9:30 PM | no email | MMD R26.1 Production Cutover Bridge (24 hours) | CIO.Legal.MMD.All; CIO.MMD.IndiaTeam; CIO.MMD.Operations; MMD.BuySide.Program.FA.BA; Legal.Tech.Ops.Leads; icmaccenture@icertis.com; Alvarez, Jacobo <jacobo.alvarez@accenture.com>; [downstream/integration apps alias]; Anand, Shweta, Adam, Denise, Maricar; sean.philip.mckeogh | - | CIO.Legal.MMD.All; CIO.MMD.IndiaTeam; CIO.MMD.Operations; MMD.BuySide.Program.FA.BA; Legal.Tech.Ops.Leads; icmaccenture@icertis.com; Alvarez, Jacobo <jacobo.alvarez@accenture.com>; [downstream/integration apps alias]; Anand, Shweta, Adam, Denise, Maricar; sean.philip.mckeogh | All day Outlook invite.
[10 empty] | Dec 12, 9:15 PM | no email | MMD R26.1 Pre-cutover / Start Call (1 hour) | > All bridge call shift-members, Ops |  |  | Same bridge used for the checkpoint and status calls.
[10 empty] | Dec 13, 1:30 PM | Ella/Ian or Jun | MMD R26.1 Cutover Status Call (20 minutes) + Send Status Email | > All bridge call shift-members |  |  | Include people here on the status emails.
[10 empty] | Dec 13, 4:25 AM | Fean/Ian or Jun | MMD R26.1 Cutover Status Call (20 minutes) + Send Status Email | > All bridge call shift-members |  | > All bridge call shift-members, Ops | CIO.Legal.MMD.Leads includes Stephen, Sergio, and Laura
[10 empty] | Dec 13, 8:10 PM | Lucho/Lau or Diego | MMD R26.1 Cutover Status Call (20 minutes) + Send Status Email | > All bridge call shift-members |  | > All bridge call shift-members
[10 empty] | Dec 14, 12:10 AM | Cami/Lau or Diego | MMD R26.1 Cutover Status Call (20 minutes) + Send Status Email | > All bridge call shift-members |  | > All bridge call shift-members
[10 empty] | Dec 14, 3:10 AM | Gaby/Lau or Diego | MMD R26.1 Cutover Status Call (20 minutes) + Send Status Email | > All bridge call shift-members |  | > All bridge call shift-members
[10 empty] | Dec 14, 5:10 AM | Diego or Ops Team | MMD R26.1 Cutover Executive Status Call (20 minutes) | > All bridge call shift-members, Jenn, Mackie, Erin, Cut, Ops, Anand, Shweta, Adam, sean.philip.mckeogh, Shiju |  | > All bridge call shift-members
[10 empty] | Dec 14, 6:25 AM | Diego or Ops Team | MMD R26.1 Smoke Test Readiness Call - Buy&Sell Side (15 minutes) | > All bridge call shift-members, smoke testers, Ops |  | > All bridge call shift-members, Jenn, Mackie, Erin, Cut, Ops, Anand, Shweta, Adam, sean.philip.mckeogh, Shiju | Send status email 20-30 min before
[10 empty] | Sep13, 9:30 PM | Shiju | MMD R26.1 Go Confirmation Email (5 mins) | >Shiju |  | > All bridge call shift-members, smoke testers, Ops
38 | Validate Data Conversion | 1.5 hrs | 37SS+30 mins |  |  | 0% | Sat 9/13/25 5:30 PM | Sat 9/13/25 7:00 PM | Sun 9/14/25 4:00 AM | Sun 9/14/25 5:30 AM | Sun 9/14/25 6:30 AM | Sun 9/14/25 8:00 AM | Sat 9/13/25 7:30 PM | Accenture team | Prasad/Tamim |  |  | Sat 6/14/25 4:45 PM | Sat 6/14/25 6:15 PM
39 | Buy Side - Accenture Write Test/Smoke test/BSR to MMD Integration | 2 hrs | 37SS+30 mins | 43,44 |  | 0% | Sat 9/13/25 5:30 PM | Sat 9/13/25 7:30 PM | Sun 9/14/25 4:00 AM | Sun 9/14/25 6:00 AM | Sun 9/14/25 6:30 AM | Sun 9/14/25 8:30 AM | Sat 9/13/25 7:30 PM | MMD Buy Side team | Lau/Diego |  |  | Sat 6/14/25 4:45 PM | Sat 6/14/25 6:45 PM
Note on E2: Briñas, Arizza: Can create Buy Side Requests and Agreements Can view rules and masterdata

## UAT Report
FY26.3 June Release
Group |  | Country | Name | Request ID | Agreement ID | Availability | Status | Day 1 | Day 2 | Day 3 | Comment | Group | Passed | Failed | In Progress | Not Started | Not Applicable | Total
LEGAL | INDIA | India | dojo.davis@accenture.com | SREQ_33461 | SMA_66065 | YES | Completed | Completed | Completed | Completed |  | CEE Legal | 12 | 0 | 0 | 0 | 0 | 12
| INDIA | India | pallavi.j.verma@accenture.com | SREQ_33458 | SMA_66093 | YES | Completed | Completed | Completed | Completed |  | INDIA Legal | 6 | 0 | 0 | 0 | 0 | 6
| CEE | Romania | oana-elena.soceanu@accenture.com | SREQ_33490 | SCC_35571 | YES | Completed | Completed | Completed | Completed |  | India Procurement | 3 | 0 | 0 | 0 | 0 | 3
| CEE | Poland | anna.mroczkowska@accenture.com | SREQ_33449 | SMA_66092 | YES | Completed | Completed | Completed | Completed |  | CEE Procurement | 3 | 0 | 0 | 0 | 0 | 3
| CEE | Romania | emilia.trandafir@accenture.com | SREQ_33469 | SMA_66069 | YES | Completed | Completed | Completed | Completed |  | FBL Procurement | 3 | 0 | 0 | 0 | 0 | 3
| CEE | Romania | ligia.s.seceleanu@accenture.com | SREQ_33485 | SMA_66068 | YES | Completed | Completed | Completed | Completed
P+ | CEE | Romania | timea.bak@accenture.com | SREQ_33463 | SMA_66094 | YES | Completed | Completed | Completed | Completed |  |  | Overall Status | Sprint # | Phase | Start Date | Initial End Date | New End Date
| FBL | France | alina-liliana.maftei@accenture.com | SREQ_33486 | SCC_35569 | YES | Completed | Completed | Completed | Completed |  |  | Completed | 4 | UAT | 2026-05-26 | 2026-05-29
| INDIA | India | ashwini.a.naik@accenture.com | SREQ_33464 | SSW_32936 | YES | Completed | Completed | Completed | Completed
FY24.2 March Release
[12 empty] | Group | Passed | Failed | In Progress | Not Started | Not Applicable | Total
| Group |  | Name | Request ID | Agreement ID |  | Status | Day 1 | Day 2 | Day 3 | Comment | UKIA Legal | 6 | 0 | 0 | 0 | 0 | 6
| UKIA Legal |  | Seceleanu, Ligia | SREQ_14733 | SMA_51299 |  | Completed | Completed | Completed | Completed |  | GALLIA Legal | 3 | 0 | 0 | 0 | 0 | 3
| UKIA Legal (BSR) |  |  | BSPR0046609 |  |  | Completed | Completed | Completed | Completed |  | NA Legal | 3 | 0 | 0 | 0 | 0 | 3
| GALLIA Legal |  | Pocania, Bianca | BSPR0046605 | SMA_51293 |  | Completed | Completed | Completed | Completed |  | India Procurement | 14 | 0 | 0 | 0 | 4 | 18
| NA Legal |  | Atul Kherde, Aboli | SREQ_14750 | SCC_24806 |  | Completed | Completed | Completed | Completed |  | PH Procurement | 8 | 0 | 0 | 0 | 1 | 9
| India Procurement |  | Mohanty, Kaushik |  |  |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | OOO on last day of testing | NA Procurement | 6 | 0 | 0 | 0 | 0 | 6
|  |  | Daniel, Magdalene | SREQ_14764 | SMA_51324 |  | Completed | Completed | Completed | Completed
|  |  | MR, Muthuramalingam |  | FIND_6104 |  | Completed | Not Applicable | Completed | Completed |  |  | Passed | Failed | In Progress | Not Started | Not Applicable | Total
|  |  | Venkatappa, Manjunatha | SREQ_14738 | SCC_24802 |  | Completed | Completed | Completed | Completed |  |  | 40 | 0 | 0 | 0 | 5 | 45
|  |  | Soman, Athul | SREQ_14706 | SMA_51258 |  | Completed | Completed | Completed | Completed |  |  | Overall Status | Sprint # | Phase | Start Date | Initial End Date | New End Date
|  |  | Hussain, Imam | SREQ_14737 | SMA_51303 |  | Completed | Completed | Completed | Completed |  |  | Completed | 8 | UAT | 2024-02-27 | 2024-02-29
| PH Procurement |  | Tongol, Princess G. | BSPR0046607 |  |  | Completed | Completed | Completed | Completed
|  |  | Narra, Franklin |  | FIND_6103 |  | Completed | Not Applicable | Completed | Completed
|  |  | Buen, Cherie Amor | BSPR0046606 | SMA_51290 |  | Completed | Completed | Completed | Completed
| NA Procurement |  | Tula Molina, Magdalena | SREQ_14760 | SSW_23829 |  | Completed | Completed | Completed | Completed
|  |  | Camarero, Daniela | SREQ_14682 | SCC_24798 |  | Completed | Completed | Completed | Completed
FY24.3 June Release
[12 empty] | Group | Passed | Failed | In Progress | Not Started | Not Applicable | Total
| Group |  | Name | Request ID | Agreement ID |  | Status | Day 1 | Day 2 | Day 3 | Comment | ASGR Legal | 3 | 0 | 0 | 0 | 0 | 3
| ASGR Legal |  | Seceleanu, Ligia | SREQ_14430 | SMA_51419 |  | Passed | Passed | Passed | Passed |  | NA Procurement | 3 | 0 | 0 | 0 | 0 | 3
| NA Procurement |  | Tula Molina, Magdalena | SREQ_14425 | SSW_23735 |  | Passed | Passed | Passed | Passed | Miguez, Cristian has been removed as a UAT tester upon his request, as he will be collaborating with Magdalena on her UAT scenario | India Procurement | 3 | 0 | 0 | 0 | 0 | 3
| India Procurement |  | Daniel, Magdalene | SREQ_14420 | SMA_51391 |  | Passed | Passed | Passed | Passed |  | PH Procurement | 12 | 0 | 0 | 0 | 0 | 12
| PH Procurement |  | Dela Cruz, Ian Jonas | SREQ_14423 | SCC_24766 |  | Passed | Passed | Passed | Passed
|  |  | Verano, Jay-ar | SSSR_1349 |  |  | Passed | Passed | Passed | Passed
|  |  | Rubin, Jean |  | FIND_6000 |  | Passed | Passed | Passed | Passed
| PH Procurement/BSR |  | Tongol, Princess G. | SREQ_14428 | SMA_51410 |  | Passed | Passed | Passed | Passed |  |  | Passed | Failed | In Progress | Not Started | Not Applicable | Total
[13 empty] | 21 | 0 | 0 | 0 | 0 | 21
[13 empty] | Overall Status | Sprint # | Phase | Start Date | Initial End Date | New End Date
[13 empty] | Completed | 11 | UAT | 2024-05-28 | 30/02/2024
FY24.4 September Release
| Group |  | Name | Request ID | Agreement ID |  | Status | Day 1 | Day 2 | Day 3 | Comment
| ASGR Legal |  | Seceleanu, Ligia |  | SMA_56111 |  | Completed | Completed | Completed | Not Applicable
[5 empty] | SMA_56113 |  | Completed | Completed | Completed | Not Applicable
|  |  | Bauer-Grass, Claudia |  | SCC_27923 |  | Completed | Completed | Completed | Not Applicable
|  |  | Wielgus, Eva |  | SMA_56116 |  | Completed | Completed | Completed | Not Applicable
| ASGR Procurement |  | Juraj Grega |  | SCC_27917 |  | Completed | Completed | Completed | Not Applicable
|  |  | Timea Bak |  | SMA_56118 |  | Completed | Completed | Completed | Not Applicable
| ICEG Procurement |  | Francesca Oreto | SREQ_18938 | SMA_56131 |  | Completed | Completed | Completed | Completed
| PH Procurement |  | Princess Tongol | SREQ_18946 | SMA_56136 |  | Completed | Completed | Completed | Completed
|  |  | Marinela Vicente | SREQ_18937 | SMA_56127 |  | Completed | Completed | Completed | Completed
|  |  | Lovelyn Juguilon | SREQ_18954 | SCC_27926 |  | Completed | Completed | Completed | Completed
|  |  | Cherie Amor Buen | SREQ_18955 | SCC_27927 |  | Completed | Completed | Completed | Completed
| INDIA Procurement |  | Magdalene Daniel | SREQ_18950 | SCC_27924 |  | Completed | Completed | Completed | Completed
| Group |  | Passed | Failed | In Progress |  | Not Started | Not Applicable | Total
| ASGR Legal |  | 8 | 0 | 0 |  | 0 | 4 | 8
| ASGR Procurement |  | 4 | 0 | 0 |  | 0 | 2 | 4
| ICEG Procurement |  | 3 | 0 | 0 |  | 0 | 0 | 3
| PH Procurement |  | 12 | 0 | 0 |  | 0 | 0 | 12
| INDIA Procurement |  | 3 | 0 | 0 |  | 0 | 0 | 3
|  |  | Passed | Failed | In Progress |  | Not Started | Not Applicable | Total
|  |  | 30 | 0 | 0 |  | 0 | 6 | 30
|  |  | Overall Status | Sprint # | Phase |  | Start Date | Initial End Date | New End Date
|  |  | Completed | 14 | UAT |  | 2024-08-27 | 2024-08-29
Note on F91: Dela Cruz, Princess Diane: SMA_53789 Created in Prod
Note on E92: Dela Cruz, Princess Diane: SREQ_15488 Created in Prod
Note on F92: Dela Cruz, Princess Diane: SSW_24502 Created in Prod

## Downtime
Submitted | Purpose | Environments | [6 empty] | Type | Frequency | Start Date | End Date | Start Date | End Date | Start Date | End Date | Status | Comments
By |  |  | Non Prod | [5 empty] | Soft or Hard
|  | PROD | PRODFIX | CS | DEV | UAT/QA | Sandbox | Sandbox2 (KYC) |  |  | Philippines | Philippines | CST | CST | India | India
Anusha/Manu Priya | R24.4 Sprint 12 - P2P - DEV to UAT |  |  |  |  | x |  |  | Hard |  |  |  | 2024-07-08 | 2024-07-09 05:11 | 2024-07-08 11:30 | 2024-07-09 15:41 | Completed
Anusha/Manu Priya | R24.4 Sprint 12 - P2P - DEV to UAT Bug Fixes |  |  |  |  | x |  |  | Hard |  |  |  | 2024-07-15 | 2024-07-15 05:11 | 2024-07-15 11:30 | 2024-07-15 15:41 | Completed
Anusha/Manu Priya | R24.4 Sprint 12- P2P - DEV to UAT Bug Fixes |  |  |  |  | x |  |  | Hard |  |  |  | 2024-07-22 | 2024-07-22 05:11 | 2024-07-22 11:30 | 2024-07-22 15:41 | Completed
Anusha/Manu Priya | R24.4 Sprint 13 - P2P - DEV to UAT |  |  |  |  | x |  |  | Hard |  |  |  | 2024-07-29 | 2024-07-29 05:11 | 2024-07-29 11:30 | 2024-07-29 15:41 | Completed
Anusha/Manu Priya | R24.4 Sprint 13- P2P - DEV to UAT Bug Fixes |  |  |  |  | x |  |  | Hard |  |  |  | 2024-08-05 | 2024-08-05 05:11 | 2024-08-05 11:30 | 2024-08-05 15:41 | Completed
Anusha/Manu Priya | R24.3 Sprint 14 - P2P - DEV to UAT |  |  |  |  | x |  |  | Hard |  |  |  | 2024-07-08 | 2024-07-09 05:11 | 2024-07-08 11:30 | 2024-07-09 15:41 | Completed
Anusha/Manu Priya | R24.4 Sprint 14 - P2P - DEV to UAT Bug Fixes |  |  |  |  | x |  |  | Hard |  |  |  | 2024-08-12 | 2024-08-12 05:11 | 2024-08-12 11:30 | 2024-08-12 15:41 | Completed
Anusha/Manu Priya | R24.4 Mock 1 P2P - UAT to Prodfix |  | x | [5 empty] | Hard |  |  |  | 2024-08-26 | 2024-08-26 05:11 | 2024-08-26 11:30 | 2024-08-26 15:41 | Completed
Anusha/Manu Priya | R24.4 Mock 2 P2P - UAT to Prodfix |  | x | [5 empty] | Hard |  |  |  | 2024-09-05 | 2024-09-05 05:11 | 2024-09-05 11:30 | 2024-09-05 15:41 | Completed
Anusha/Manu Priya | R 24.4 Go Live | x | [6 empty] | Hard |  |  |  | 2024-09-16 | 2024-09-16 05:11 | 2024-09-16 11:30 | 2024-09-16 15:41 | Not Started
Anusha/Durga | R26.3 Sprint P2P - Dev to UAT |  |  |  |  | x |  |  | Hard |  | 2026-04-06 14:15 | 2026-04-06 19:25 | 2026-04-06 01:15 | 2026-04-06 06:25 | 2026-04-06 11:45 | 2026-04-06 16:55 | Completed
Anusha/Durga | R26.3 Sprint P2P - Dev to UAT |  |  |  |  | x |  |  | Hard |  | 2026-04-20 14:30 | 2026-04-20 18:30 | 2026-04-20 00:30 | 2026-04-20 05:30 | 2026-04-20 12:00 | 2026-04-20 16:00 | Not Started
Anusha/Durga | R26.3 Sprint P2P - Dev to UAT |  |  |  |  | x |  |  | Hard |  | 2026-05-04 14:30 | 2026-05-04 18:30 | 2026-05-04 00:30 | 2026-05-04 05:30 | 2026-05-04 12:00 | 2026-05-04 16:00 | Not Started
Anusha/Durga | R26.3 Sprint P2P - Dev to UAT |  |  |  |  | x |  |  | Hard |  | 2026-05-18 14:30 | 2026-05-18 18:30 | 2026-05-18 00:30 | 2026-05-18 05:30 | 2026-05-18 12:00 | 2026-05-18 16:00 | Not Started
Anusha/Durga | R26.3 Perf P2P - UAT to Perf | [5 empty] | x |  | Hard |  | 2026-05-19 14:30 | 2026-05-19 18:30 | 2026-05-19 00:30 | 2026-05-19 05:30 | 2026-05-19 12:00 | 2026-05-19 16:00 | Not Started
Anusha/Durga | R26.3 Mock1 P2P - UAT to Prodfix |  | x | [5 empty] | Hard |  | 2026-05-25 14:30 | 2026-05-25 18:30 | 2026-05-25 00:30 | 2026-05-25 05:30 | 2026-05-25 12:00 | 2026-05-25 16:00 | Not Started
Anusha/Durga | R26.3 Mock2 P2P - UAT to Prodfix |  | x | [5 empty] | Hard |  | 2026-06-04 14:30 | 2026-06-04 18:30 | 2026-06-04 00:30 | 2026-06-04 05:30 | 2026-06-04 12:00 | 2026-06-04 16:00 | Not Started
Anusha/Durga | R26.3 Go - Live | x | [6 empty] | Hard
DOWNTIME LINK | MMD Downtime Log_v3.xlsx (accenture.com)
Additional Downtime |  | PH Time |  |  |  |  | Sample Formula
Environment | Date | Start Time | End Time | Total Time (Hrs) |  |  | =TEXT(D22-C22, "h:mm")
Formulas:
Start Date = IF([Start Date]="","",[Start Date]+ 11.5/24)
End Date = IF([End Date]="","",[End Date]+ 10.5/24)

## BSR Access
Environment | BSR ¦ E2E (SBOX7) |  |  | Market Unit | Country Name | MMD Available
| BSR ¦ SNOW (SBOX7) |  |  | Nordic | 2023-02-01
Country | All Countries/Global | NA
| United States |  |  | Iberia | Andorra | 2023-12-01
| Canada |  |  |  | Israel
| Puerto Rico |  |  |  | Portugal
| Philippines | PH |  |  | Spain
| France | FR |  | Nordic | Denmark | 2023-09-01
| Belgium |  |  |  | Finland
| Luxembourg |  |  |  | Latvia
| Australia | UKI |  |  | Norway
| Ireland |  |  |  | Sweden
| Mauritius |  |  | Greater China | Greater China
| Netherlands |  |  | Africa | South Africa | 2022-06-01
| New Zealand |  |  |  | Botswana
| hn |  |  |  | Kenya
| South Africa |  |  | Middle East | Bahrain
| Botswana |  |  |  | Qatar
| Kenya |  |  |  | Saudi Arabia
| Bahrain |  |  |  | United Arab Emirates
| Qatar |  |  |  | Egypt
| Saudi Arabia |  |  | SEA | Brunei
| United Arab Emirates |  |  |  | Indonesia
| Egypt |  |  |  | Malaysia
| Brunei |  |  |  | Singapore
| Indonesia |  |  |  | Thailand
| Malaysia |  |  |  | Vietnam
| Singapore |  |  | ANZ | Australia | 2022-03-01
| Thailand |  |  |  | New Zealand
| Vietnam |  |  | Gallia | France | 2022-02-01
| Morocco |  |  |  | Belgium
| Spain |  |  |  | Netherlands
| Portugal |  |  |  | Luxembourg
| Andorra |  |  |  | Mauritius
| Israel |  |  |  | Morocco
User | jofinny.cervera |  | Not Started | UKI | United Kingdom
| sheena.m.barcillano |  | Not Started
| ma.cristine.s.aban@accenture.com |  | Not Started
| jhoanna.m.montales |  | Not Started |  | Ireland
| jonathan.carpio@accenture.com |  | Not Started | NA | Puerto Rico
| guna.r.jagadeeswaran@accenture.com |  | Not Started | Philippines | Philippines | 2021-06-01
| jhea.m.m.magoncia@accenture.com |  | Not Started | NA | Canada
| izzy-jhoy.padilla@accenture.com |  | Not Started |  | United States
| elealeh.tan@accenture.com |  | Not Started |  | All Countries/Global
| ma.cristine.s.aban@accenture.com |  | Not Started
| astharani.bastia@accenture.com |  | Not Started | ICEG | Bulgaria
| arianne.c.abuque@accenture.com |  | Not Started |  | Czech Republic
Greece
Hungary
Italy
|  | Bulgaria |  |  | Poland
|  | Austria |  |  | Romania
|  | Turkey |  |  | Slovakia
|  | Switzerland |  | ASG | Austria
|  | Czech Republic |  |  | Germany
|  | Hungary |  |  | Switzerland
Turkey
|  |  |  | Japan | Japan

## MMD-ADO Access
QA ENVIRONMENT ACCESS |  |  |  |  | PRODFIX ENVIRONMENT ACCESS |  |  |  | QA ENVIRONMENT ACCESS |  |  |  | E
Full Name | EID | Can Create Buy Side Request and Agreements? (Refer to B16) | Can view Rules? (Refer to B44) | Has Log In as button? | EID | Can Create Request and Agreement? | Can View Rules | Has Log in as? | EID | Can Create Request and Agreement? | Can View Rules | Has Log in as? | EID | Need MMD Add-in Access?
ma.cristine.s.aban@accenture.com
Jhoanna Montales | jhoanna.m.montales | Yes | No | No | jhoanna.m.montales | Yes | Yes | Yes | ma.cristine.s.aban@accenture.com |  |  |  | ma.cristine.s.aban@accenture.com
Mayee Ann Lopez | mayee.ann.lopez | Yes | No | No | jonathan.carpio@accenture.com | Yes | Yes | Yes | jhoanna.m.montales | Yes | Yes | Yes | jhoanna.m.montales
John O'Neill | john.m.oneill | Yes | No | No | guna.r.jagadeeswaran@accenture.com | Yes | Yes | Yes | jonathan.carpio@accenture.com | Yes | Yes | Yes | jonathan.carpio@accenture.com
Jim Panambo | jim.panambo | Yes | No | No | jhea.m.m.magoncia@accenture.com | Yes | Yes | Yes | guna.r.jagadeeswaran@accenture.com | Yes | Yes | Yes | guna.r.jagadeeswaran@accenture.com
Kimberly Mediavillo | kimberly.mediavillo | Yes | No | No | izzy-jhoy.padilla@accenture.com | Yes | Yes | Yes | jhea.m.m.magoncia@accenture.com | Yes | Yes | Yes | jhea.m.m.magoncia@accenture.com
Princess Diane Medroso | princess.d.medroso | Yes | No | No | elealeh.tan@accenture.com | Yes |  | Yes | izzy-jhoy.padilla@accenture.com | Yes | Yes | Yes | izzy-jhoy.padilla@accenture.com
Jeanne Pauline Garlota | jeanne.p.garlota | Yes | No | No | astharani.bastia@accenture.com | Yes | Yes | Yes | elealeh.tan@accenture.com | Yes |  | Yes | elealeh.tan@accenture.com
Angelica Tindoc | angelica.tindoc | Yes | No | No | arianne.c.abuque@accenture.com | Yes | Yes | Yes | astharani.bastia@accenture.com | Yes | Yes | Yes | astharani.bastia@accenture.com
MMD BuySideTstAuto01 | T48176.01.BuyTstAuto | Yes | No | No |  |  |  |  | arianne.c.abuque@accenture.com | Yes | Yes | Yes | arianne.c.abuque@accenture.com
Can Create Buy Side Request and Agreements?
ADO ACCESS
[5 empty] | EID | Can View Dashboard
[5 empty] | ma.cristine.s.aban@accenture.com | Yes
[5 empty] | jhoanna.m.montales | Yes
[5 empty] | jonathan.carpio@accenture.com | Yes
[5 empty] | guna.r.jagadeeswaran@accenture.com | Yes
[5 empty] | arianne.c.abuque@accenture.com | No
[5 empty] | elealeh.tan@accenture.com | Yes
[5 empty] | izzy-jhoy.padilla@accenture.com | Yes
[5 empty] | jhea.m.m.magoncia@accenture.com | No
[5 empty] | astharani.bastia@accenture.com | No
Can view Rules?

## Sheet1 (hidden)
Task Name | Total Duration | CDT Start | CDT Finish | IST Start | IST Finish | Phil Start date | Phil End date
Buy Side - Accenture Write Test/Smoke test/BSR to MMD Integration | 3 hrs | Sat 6/13/26 3:15 PM | Sat 6/13/26 6:15 PM | Sun 6/14/26 1:45 AM | Sun 6/14/26 4:45 AM | Sun 6/14/26 4:15 AM | Sun 6/14/26 7:15 AM
Overall Status | Sprint # | Phase | End Date | New End Date
Completed | 15 | Sprint 15 Preparation | 2026-04-03
Completed | 15 | Sprint 15 Test Execution | 2026-04-17
Completed | 16 | Sprint 16 Preparation | 2026-04-17
Completed | 16 | Sprint 16 Test Execution | 2026-05-01
Completed | 17 | Sprint 17 Preparation | 2026-05-01
Completed | 17 | Sprint 17 Test Execution | 2026-05-15
Completed | 18 | Sprint 18 Preparation | 2026-05-15
Completed | 18 | Sprint 18 Test Execution | 2026-05-29 | 2026-06-05
Completed | 18 | UAT Execution | 2026-05-29
Completed | 18 | Mock Test Preparation | 2026-05-29
Completed | 18 | Mock Testing | 2026-05-29 | 2026-06-04
KTLO Bugs​ | ADO ID ​ | Status​ | Sprint #​ | Comment​
[MMD BuySide][R26.2 QA, PRDFIX] - Excess signatory is showing in the signatory field​ | 1041077​ | Closed - Verified​ | 15​ | Backlog Defect​
[Buy Side R26.2 S14] - Supplier Permitted Termination Date is not updating in Save Search in agreement list​ | 1044636​ | Closed - Verified​ | 15​ | Backlog Defect​
[MMD BuySide][R26.3] Attribute Value discrepancy for "Is Contract Admin Present" for business status Assigned or Assignment Pending is displayed in Saved Search​ | 1061641​ | Closed - Verified​ | 16​ | Backlog Defect​
[BuySide R26.3 QA/Prodfix] Unable to Validate for Signature Due to Missing Mandatory Supplier Details​ | 1083765​ | Closed - Verified​ | 17​ | Product Testing Defect​
[Buy Side - R26.3 QA] - Delegated Spend Acquisition Attribute Field Is Visible When Condition Is Not Met​ | 1087190​ | Closed - Verified​ | 17​ | Product Testing Defect​
[MMD Buy Side R26.3 S18] - Unable to get supplier details​ | 1100995​ | Closed - Verified​ | 18​ | Product Testing Defect​
[Buy Side - R26.3] Supplier Preferred Name values “Advisor” and “Agent” are not translated to Chinese(Simplified) across all agreement types: SMA, SCC, and SSW.​ | 1110287​ | Closed - Verified​ | 18​ | Product Testing Defect​
[Buy Side - 26.3] Agreements not getting expired even though end date is passed​ | 1118820​ | Closed - Verified​ | 19​ | Product Testing Defect​
[Buy Side - Release QA] Required Association for Supplier Order or SOW​ | 1129174​ | Closed - Verified​ | 19​ | Product Testing Defect​
[Buy Side - R26.3][Prdfix] Closing the pop-up error message the screen does not focus to date entry field which has an error​ | 1129099​ | Closed - Verified​ | 19​ | Mock Testing Defect​
[Buy FY26.3] [QA] Attribute label is displayed incorrectly in category attributes (shows technical field name)​ | 1119900​ | Closed - Verified​ | 19​ | Product Testing Defect​
[Buy Side - 26.3] Category Group dropdown does not load on initial click of “Get Categories” button​ | 1128512​ | Closed - Verified​ | 19​ | Product Testing Defect​
[Buy Side - R26.3] Purchase Category is not match both QA and Prodfix​ | 1129749​ | Closed - Verified​ | 19​ | Mock Testing Defect​
[Buy Side - R26.3] Error while retrieving data from MMS when validating Opportunity ID on Create Contract Request | 1131503 | Closed - Verified​ | 20 | Product Testing Defect​
[Buy Side - R26.3] [SCC Agreement] Missing Recipient Name in “For Your Review” Email Notification | 1131593 | Closed - Verified​ | 20 | Product Testing Defect​
TPRM Bugs​ | ADO ID ​ | Status​ | Sprint #​ | Comment​
[MMD Buy Side - R26.3 QA] - Coupa ID values are not integrating upon triggering of the Coupa ID​ | 1108153​ | Closed - Verified​ | 18​ | Product Testing Defect​
Supplier PII Cross-Border Transfer New attribute dropdown displays 2 extra Countries​ | 1117652​ | Closed - Verified​ | 19​ | Product Testing Defect​